## WebpageOverrides
Key | Value

## MEPReadiness
LOCATION | SHEARING | PRE-CLEAN & DES AREA | IMAGING CLEAN ROOM AREA-8A,8B | IMAGING CLEAN ROOM AREA-8 | ARTWORK CLEAN ROOM | AOI | MLB | CNC DRILLING | COPPER PLATING AREA | SM OVEN & PRE-CLEAN AREA | SM CLEAN ROOM AREA | LP AREA | SCREEN ROOM | SURFACE FINISH AREA | CNC ROUTING | BBT | FI | CHEMICAL LAB | PHYSICAL LAB | PACKING
Priority for secondary connections | 18 | 1 | 7 | 8 | 19 | 9 | 4 | 5 | 2 | 3 | 12 | 13 | 20 | 10 | 6 | 11 | 16 | 14 | 15 | 17
MACHINE DISPATCH STATUS | AFTER ADVANCE PAYMENT | 20-05-2026-BATCH1 | ARRIVED | ARRIVED | ADVANCE PAYMENT DONE | ADVANCE PAYMENT DONE | LAUFFER ARRIVED AND BF: 20-05-2026 | BATCH 1 ARRIVED | 20-05-2026-BATCH1 | 20-05-2026-BATCH1 - UCE | ARRIVED | AFTER ADVANCE PAYMENT | AFTER ADVANCE PAYMENT | PENTA ARRIVED 20-05-2026-BATCH1- UCE | ARRIVED | ATG-ADVANCE PAYMENT DONE BBT -ADVANCE NOT DONE | PAYMENT NOT DONE |  |  | PAYMENT NOT DONE
CHILLER UNIT MAIN SUPPLY | NA | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | NA | NA | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | NA | NA | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | NA | NA | NA | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | NA | NA
FLOOR READINESS WITH EPOXY | 2026-05-30 | DONE | DONE | DONE | DONE | DONE | Done | Done | DONE | DONE | DONE | DONE | DONE | DONE | Done | Done | 30-05-2026 15-06-2026 | 30-05-2026 15-06-2026 | 30-05-2026 15-06-2026 | 30-05-2026 15-06-2026
CLEAN ROOM READINESS -READY FOR M/C ERECTION | NA | NA | DONE | DONE | DONE | NA | DONE | NA | NA | NA | DONE | NA | NA | NA | NA | NA | NA | NA | NA | NA
CLEAN ROOM READINESS -FINAL HANDOVER | NA | NA | 30-06-2026 25-07-2026 | 30-06-2026 25-07-2026 | 30-06-2026 08-07-2026 25-07-2026 | NA | 30-06-2026 04-07-2026 25-07-2026 | NA | NA | NA | 30-06-2026 12-07-2026 25-07-2026 | NA | NA | NA | NA | NA | NA | NA | NA | NA
AHU SYSTEM | 10-06-2026 20-06-2026 Revised 20-07-2026 | NA | 10-06-2026 20-06-2026 Revised 20-07-2026 | 10-06-2026 20-06-2026 Revised 20-07-2026 | 10-06-2026 20-06-2026 Revised 20-07-2026 | 10-06-2026 20-06-2026 Revised 20-07-2026 | 10-06-2026 20-06-2026 Revised 20-07-2026 | 10-06-2026 20-06-2026 Revised 20-07-2026 | 10-06-2026 20-06-2026 Revised 20-07-2026 | NA | 10-06-2026 20-06-2026 Revised 20-07-2026 | 10-06-2026 20-06-2026 Revised 20-07-2026 | 10-06-2026 20-06-2026 Revised 20-07-2026 | NA | 10-06-2026 20-06-2026 Revised 20-07-2026 | 10-06-2026 20-06-2026 Revised 20-07-2026 | 10-06-2026 20-06-2026 Revised 20-07-2026 |  | 10-06-2026 20-06-2026 Revised 20-07-2026 | 10-06-2026 20-06-2026 Revised 20-07-2026
PUFF PANEL PARTITION ERECTION AND READINESS | 6/20/2026 25/7/2026 | NA | 25-06-2026 done | 25-06-2026 done | 25-06-2026 done | 6/20/2026 10/7/2026 | 25-06-2026 done | 6/20/2026 7/7/2026 | 2026-07-07 | NO CLARITY | 2026-06-25 | 7/4/2026 13/7/2026 | 6/20/2026 10/7/2026 | NA | 6/20/2026 7/7/2026 | 2026-07-13 | 2026-07-13 | 2026-06-26 | 2026-06-26 | 2026-07-17
DUST COLLECTOR READINESS PRIMARY | DONE | NA | NA | NA | NA | NA | NA | DONE | NA | NA | NA | NA | NA | NA | 2026-05-30 | NA | NA | NA | NA | NA
DUST COLLECTOR READINESS SECONDARY | DURING MACHINE INSTALLATION | NA | NA | NA | NA | NA | NA | DURING MACHINE INSTALLATION | NA | NA | NA | NA | NA | NA | DURING MACHINE INSTALLATION | NA | NA | NA | NA | NA
FUME SCRUBBER READINESS | NA | 2026-07-15 | NA | NA | NA | NA | 2026-07-15 | NA | 2026-07-15 | 2026-07-15 | NA | NA | NA | 2026-07-15 | NA | NA | NA | 2026-07-15 | NA | NA
COMPRESSED AIR SYSTEM-PRIMARY CONNECTIONS | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE | 10-06-2026 15-06-2026 DONE
COMPRESSED AIR SYSTEM-SECONDARY CONNECTIONS | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026 | 05-07-2026 20-07-2026
CHILLER READINESS- PRIMARY CONNECTION | NA | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | NA | NA | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | NA | NA | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 12-07-2026 | NA | NA | NA | 10-06-2026/ 20-06-2026/ Revised 30-06-2026 | NA | NA
CHILLER READINESS-SECONDARY CONNECTION | NA | 05-07-2026 20-07-2026 with water | 05-07-2026 20-07-2026 with water | 05-07-2026 20-07-2026 with water | NA | NA | 05-07-2026 20-07-2026 with water | 05-07-2026 20-07-2026 with water | 05-07-2026 20-07-2026 with water | 05-07-2026 20-07-2026 with water | 05-07-2026 20-07-2026 with water | NA | NA | 05-07-2026 20-07-2026 with water | NA | NA | NA | 2026-07-05 | NA | NA
ELECTRICAL POWER-PRIMARY CONNECTION | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done | 10-06-2026 done
ELECTRICAL POWER- SECONDARY CONNECTION | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-25 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15
DG | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done | 30-05-2026 10-06-2026 15-06-2026 done
DI & RO WATER SUPPLY PRIMARY CONNECTIONS | NA | 31-05-2026 REVISED 26-06-2026 done | 31-05-2026 done | 31-05-2026 REVISED 26-06-2026 done | 31-05-2026 REVISED 26-06-2026 done | NA | 31-05-2026 REVISED 26-06-2026 done | NA | 31-05-2026 REVISED 26-06-2026 done | 31-05-2026 REVISED 26-06-2026 done | 31-05-2026 REVISED 26-06-2026 done | 31-05-2026 REVISED 26-06-2026 done | 31-05-2026 REVISED 26-06-2026 done | 31-05-2026 REVISED 26-06-2026 done | 31-05-2026 REVISED 26-06-2026 done | 31-05-2026 REVISED 26-06-2026 done | 31-05-2026 REVISED 26-06-2026 done | NA | NA | NA
DI & RO WATER SUPPLY SECONDARY CONNECTIONS | NA | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | NA | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | 2026-07-15 | NA | NA | NA
FIRE FIGHTING SYSTEM | DEPENDS ON PUFF PANEL | DONE | DONE | DONE | 20-05-2026/ 30-05-2026 10-06-2026- done | DONE | 30-05-2026 10-06-2026 done | DONE | DONE | DEPENDS ON PUFF PANEL | 30-05-2026 10-06-2026 done | DEPENDS ON PUFF PANEL | DEPENDS ON PUFF PANEL | DONE | DONE | DEPENDS ON PUFF PANEL | DEPENDS ON PUFF PANEL | DEPENDS ON PUFF PANEL | DEPENDS ON PUFF PANEL | DEPENDS ON PUFF PANEL
ETP DRAIN CONNECTION READINESS | NA | 20-05-2026/ revised 28-05-2026 : DONE | 20-05-2026/ revised 28-05-2026 : DONE | 20-05-2026/ revised 28-05-2026 : DONE | 20-05-2026/ revised 28-05-2026 : DONE | NA | 20-05-2026/ revised 28-05-2026 : DONE | NA | 20-05-2026/ revised 28-05-2026 : DONE | 20-05-2026/ revised 28-05-2026 : DONE | 20-05-2026/ revised 28-05-2026 : DONE | 20-05-2026/ revised 28-05-2026 : DONE | 20-05-2026/ revised 28-05-2026 : DONE | 20-05-2026/ revised 28-05-2026 : DONE | NA | NA | NA | NA | NA | NA
IT INFRA | 27-07-2026 T 27-08-2026 P | 06-07-2026 T 06-08-2026 P | 06-07-2026 T 06-08-2026 P | 06-07-2026 T 06-08-2026 P | 27-07-2026 T 27-08-2026 P | 13-07-2026 T 13-08-2026 P | 07-07-2026 T 07-08-2026 P | 15-07-2026 T 15-08-2026 P | 07-07-2026 T 07-08-2026 P | NA | 15-07-2026 T 15-08-2026 P | 20-07-2026 T 20-08-2026 P | NA | 11-07-2026 T 11-08-2026 P | 15-07-2026 T 15-08-2026 P | 27-07-2026 T 27-08-2026 P | 27-07-2026 T 27-08-2026 P | 27-07-2026 T 27-08-2026 P | 27-07-2026 T 27-08-2026 P | 27-07-2026 T 27-08-2026 P
DEPT READY FOR INSTALLATION

## PendingEquipments
Capex Set | New Capex No | Department | Machine name | Qty. of Machines | Updated Supplier | Priority | Lead Time (in wks) | Transit Time (wks) | Total Lead Time (wks) | Remarks/Inco Terms | Status
New | New | Wet Process | Copper Via Filling Line | 1 |  | 1 | 14 | 3 | 17 |  | Under Finalisation
4 | Under Finalization | WP (Final Finish) | ENEPIG Line | 1 |  | 2 | 14 | 3 | 17 | - | Under Finalisation
New | 34 | LAB Equipments | Microscope for Defect Analysis | 1 | Carl Zeiss | 3 | 12 | 1 | 13 | EXW Sri-City (FTWZ) | PO Released
1 | 7 | Legend | Ink Jet Printer for Legend Printing | 2 | Kewei, China | 4 | 8 | 3 | 11 | - | PO Released
2 | 13 | Photo Plotting | AOI Machine for Film Inspection with Installation & Training | 1 | CIMS, China | 5 | 8 | 3 | 11 | FOB Shanghai | PO Released
New | 21 | LAB Equipments | X-Section Grinding (BAINPOL - VTD-8" ID - Double Disc Polisher | 1 | Metco | 6 | 10 | 1 | 11 | From Ambatur, Chennai | PO Released
4 | 37 | Packing | Water Wash Line | 1 | Kewei, China | 7 | 8 | 3 | 11 | FOB | PO Released
1 | 1 | Legend | Horizontal Printer | 2 | Kewei, China | 8 | 6 | 3 | 9 | FOB | PO Released
1 | 3 | PISM | Horizontal Printer - Automatic | 2 | Kewei, China | 9 | 6 | 3 | 9 | FOB | PO Released
1 | 9 | BBT | Universal BBT Tester | 2 | Kewei, China | 10 | 6 | 3 | 9 | FOB | PO Released
2 | 11 | Automations | Loader & Unloader systems for Horizontal Conveyorised equipments | 30 | Kewei, China | 11 | 6 | 3 | 9 | FOB | PO Released
2 | 16 | Box Oven | Box Oven for Inner Layer Baking (With 6 Trey) | 1 | GP | 12 | 6 | 3 | 9 | May End | PO released (Condition Payment within March)
2 | 16 | Via Filling (Plugging) | Box Oven for Filled Via Curing | 1 | GP | 13 | 6 | 3 | 9 | May End | PO released (Condition Payment within March)
2 | 17 | PISM | Curing Oven (Box / Conveyrised) for Solder Mask Tack Dry | 2 | GP | 14 | 6 | 3 | 9 | May End | PO Released
2 | 17 | PISM | Curing Oven (Box / Conveyrised) for Solder Mask Final Curing | 2 | GP | 15 | 6 | 3 | 9 | May End | PO Released
3 | 18 | LAB Equipments | Microscope for PTH Coverage Check (Backlight test) --> CKX 53 (Olympus | 1 | I R Tech (Olympus) | 16 | 8 | 1 | 9 |  | PO Released
3 | 18 | LAB Equipments | Microscope (1000x Magnification) --> BX53M (Olympus) | 1 | I R Tech (Olympus) | 17 | 8 | 1 | 9 |  | PO Released
1 | 10 | CNC Drilling | Hole AOI checker (Drill Shift, Cpk check) | 1 |  | 18 | 8 | 0 | 8 |  | Under Finalisation
2 | 26 | LAB Equipments | Hi Pot Tester | 1 | Integrated Services & Consultancy | 19 | 8 | 0 | 8 | FOR Destination | PO Released
4 | Under Finalization | Via Filling (Plugging) | Via Filling Hole Inspection Machine | 1 |  | 20 | 4 | 4 | 8 |  | Under Finalisation
1 | 1 | CNC Drilling | Drill Ring Setting Machine | 1 | Kewei, China | 21 | 4 | 3 | 7 | FOB | PO Released
1 | 1 | CNC Drilling | Double Side Surface Grinding Machine with Loader & Unloader | 1 | Kewei, China | 22 | 4 | 3 | 7 | FOB | PO Released
1 | 1 | CNC Routing | V-Grooving Depth Checkler | 2 | Kewei, China | 23 | 4 | 3 | 7 | FOB | PO Released
1 | 1 | CNC Routing | V-Grooving Machine (Jump Score) | 2 | Kewei, China | 24 | 4 | 3 | 7 | FOB | PO Released
1 | 1 | CNC Routing | V-Grooving Machine (Multi Ctter Machine) 6 Top / 6 Bottom | 1 | Kewei, China | 25 | 4 | 3 | 7 | FOB | PO Released
1 | 1 | PISM | Ink Mixer | 2 | Kewei, China | 26 | 4 | 3 | 7 | FOB | PO Released
1 | 1 | Screen Room | Screen Exposure | 1 | Kewei, China | 27 | 4 | 3 | 7 | FOB | PO Released
1 | 1 | Screen Room | Drying Oven | 1 | Kewei, China | 28 | 4 | 3 | 7 | FOB | PO Released
1 | 1 | Screen Room | Screen Stretching Unit | 1 | Kewei, China | 29 | 4 | 3 | 7 | FOB | PO Released
1 | 1 | Screen Room | Screen Coater Double Side | 1 | Kewei, China | 30 | 4 | 3 | 7 | FOB | PO Released
1 | 1 | Screen Room | Screen Washing Unit | 1 | Kewei, China | 31 | 4 | 3 | 7 | FOB | PO Released
1 | 1 | Screen Room | Screen Developing Unit | 1 | Kewei, China | 32 | 4 | 3 | 7 | FOB | PO Released
1 | 1 | Shearing | Flash Routing Machine | 2 | Kewei, China | 33 | 4 | 3 | 7 | FOB | PO Released
1 | 2 | Photo Plotting | Film Punching Machine | 1 | Kewei, China | 34 | 4 | 3 | 7 | FOB | PO Released
1 | 2 | Photo Plotting | Film Laminator | 1 | Kewei, China | 35 | 4 | 3 | 7 | FOB | PO Released
1 | 2 | Shearing | Corner Rounding Machine | 1 | Kewei, China | 36 | 4 | 3 | 7 | FOB | PO Released
1 | 2 | Shearing | Motorised Shearing Machine | 1 | Kewei, China | 37 | 4 | 3 | 7 | FOB | PO Released
1 | 2 | Shearing | Stack Pinning / De pinning Machine | 1 | Kewei, China | 38 | 4 | 3 | 7 | FOB | PO Released
1 | 2 | Shearing | Roller Cutting Machine | 1 | Kewei, China | 39 | 4 | 3 | 7 | FOB | PO Released
1 | 2 | Shearing | Edge Beveling Machine | 1 | Kewei, China | 40 | 4 | 3 | 7 | FOB | PO Released
1 | 4 | CNC Drilling | Laser Drill Hole Checker | 2 | Zhengyee, China | 41 | 4 | 3 | 7 | FOB China | PO Released
1 | 8 | PISM | Vertical Printer | 2 | Taiyo Circuit Tech | 42 | 4 | 3 | 7 |  | PO Released
2 | 11 | LAB Equipments | Sample Cutting machine | 1 | Kewei, China | 43 | 4 | 3 | 7 | FOB | PO Released
2 | 11 | Packing | Vaccum Packing Machine | 2 | Kewei, China | 44 | 4 | 3 | 7 | FOB | PO Released
2 | 11 | Packing | Starpping Machine | 1 | Kewei, China | 45 | 4 | 3 | 7 | FOB | PO Released
2 | 11 | Packing | Wrapping Machine PVC Shrink Wrap | 1 | Kewei, China | 46 | 4 | 3 | 7 | FOB | PO Released
2 | 11 | PISM | UV Curing Machine for UV Bump prior to Surface Finish | 1 | Kewei, China | 47 | 4 | 3 | 7 | FOB | PO Released
2 | 15 | LAB Equipments | Solderability Testing Pot (Leaded & Lead Free) | 2 | Zhengyee Summit, China | 48 | 4 | 3 | 7 | FOB China | PO Released
2 | 15 | LAB Equipments | Ionic Contamination Tester | 1 | Zhengyee Summit, China | 49 | 4 | 3 | 7 | FOB China | PO Released
2 | 15 | LAB Equipments | XY Coordinator / Visual Inspection Machine | 1 | Zhengyee Summit, China | 50 | 4 | 3 | 7 | FOB China | PO Released
4 | 22 | LAB Equipments | Gel Timer | 1 | Kewei, China | 51 | 4 | 3 | 7 | FOB | PO Released
4 | 22 | LAB Equipments | Digital Viscometer | 1 | Kewei, China | 52 | 4 | 3 | 7 | FOB | PO Released
4 | 22 | LAB Equipments | PCB Thickness measurement unit | 1 | Kewei, China | 53 | 4 | 3 | 7 | FOB | PO Released
4 | 23 | Final Inspection | Line Width Tester | 1 | Kewei, China | 54 | 4 | 3 | 7 | FOB | PO Released
4 | 23 | Final Inspection | Magnifer Lens upto 10x for Final Inspection | 35 | Kewei, China | 55 | 4 | 3 | 7 | FOB | PO Released
4 | 23 | Final Inspection | Lux Measuring Equipment | 2 | Kewei, China | 56 | 4 | 3 | 7 | FOB | PO Released
4 | 24 | Yellow Room (I/L & O/L) | Dust Particle Measurement Instrument for clean rooms | 2 | Kewei, China | 57 | 4 | 3 | 7 | FOB | PO Released
4 | 24 | Yellow Room (I/L & O/L) | UV Integrator | 1 | Kewei, China | 58 | 4 | 3 | 7 | FOB | PO Released
New | 25 | LAB Equipments | Emery Paper Storage Racks | 1 | Metco | 59 | 6 | 1 | 7 | From Ambatur, Chennai | PO Released
New | 25 | LAB Equipments | Disc & Cloth Storage Rack | 1 | Metco | 60 | 6 | 1 | 7 | From Ambatur, Chennai | PO Released
New | 25 | LAB Equipments | Specimen Storage Cabinet | 1 | Metco | 61 | 6 | 1 | 7 | From Ambatur, Chennai | PO Released
New | 25 | LAB Equipments | Technomat Pressure Polymerization Device | 1 | Metco | 62 | 6 | 1 | 7 | From Ambatur, Chennai | PO Released
2 | 27 | LAB Equipments | Peel & Pull Strength Tester | 1 | Zhengyee, China | 63 | 4 | 3 | 7 | FOB China | PO Released
New | 35 | LAB Equipments | Digital Inspection | 15 | Kewei, China | 64 | 4 | 3 | 7 | FOB | PO Released
New | 35 | LAB Equipments | Digital Thickness Gauge (CCL Cu thickness tester) | 3 | Kewei, China | 65 | 4 | 3 | 7 | FOB | PO Released
New | 35 | LAB Equipments | Foldable Magnifier Lens (10x) for Final Inspection | 20 | Kewei, China | 66 | 4 | 3 | 7 | FOB | PO Released
New | 35 | LAB Equipments | Foldable Magnifier lens (10x) with pointer and Scale | 30 | Kewei, China | 67 | 4 | 3 | 7 | FOB | PO Released
New | 35 | LAB Equipments | Pencil Hardness Tester for SM | 1 | Kewei, China | 68 | 4 | 3 | 7 | FOB | PO Released
New | 35 | LAB Equipments | Dual Digital temp. controlled solder station with hot air gun | 3 | Kewei, China | 69 | 4 | 3 | 7 | FOB | PO Released
1 | 6 | Final Inspection | AVI Machine for Final Inspection | 2 | CTS Industries Pte Ltd (Screen, Singapore) | 70 | 6 | 0 | 6 | CIF Chennai | PO Released
2 | 12 | LAB Equipments | XRF Instruments for Surface Coating Check | 1 | Hitachi Hitech, Japan | 71 | 6 | 0 | 6 | CIF Chennai | PO Released
2 | 12 | LAB Equipments | CMI Intrument for Online Hole Copper Checking Hand Held Unit | 1 | Hitachi Hitech, Japan | 72 | 6 | 0 | 6 | CIF Chennai | PO Released
2 | 12 | LAB Equipments | CMI Equipments for Table Top Hole / Surface Copper Check | 1 | Hitachi Hitech, Japan | 73 | 6 | 0 | 6 | CIF Chennai | PO Released
2 | 12 | LAB Equipments | CMI 165 - Handheld Surface Copper Guage | 1 | Hitachi Hitech, Japan | 74 | 6 | 0 | 6 | CIF Chennai | PO Released
2 | 12 | LAB Equipments | Freight & Insurnce (for XRF, Hitachi Hitech) | 1 | Hitachi Hitech, Japan | 75 | 6 | 0 | 6 | CIF Chennai | PO Released
3 | 20 | LAB Equipments | AAS System for Chemical Analysis | 1 | Agilent | 76 | 6 | 0 | 6 | DDP | PO Released
New | 38 | LAB SET-UP (FURNITURE) | Capex 2/2 | 1 | PCAT | 77 | 6 | 0 | 6 |  | PO Released
1 | 5 | CNC Drilling | X-Ray Inspection Machine for Multi Layer PCBs | 1 | Glenbrook Technology | 78 | 2 | 2 | 4 | EXW New Jersey, US | PO Released
3 | 19 | LAB Equipments | UV Spectrometer | 1 | Toshvin, India | 79 | 4 | 0 | 4 | FOR Destination | PO Released
New | 38 | LAB SET-UP (FURNITURE) | Capex 1/2 | 1 | PCAT | 80 | 4 | 0 | 4 |  | PO Released
New | Done (Numbering Pending) | LAB Equipments | Hull Cell system --> New Capex with new line items to be created | 1 | Komal Agencies | 81 | 2 | 2 | 4 |  | Under Finalisation
4 | Pending | Utility | SS Trolly for PCB Panel Movement | 400 |  | 82 | 2 | 2 | 4 |  | Under Finalisation
New | 33 | LAB Equipments | ATX224R - Analytical Balance | 1 | Precision Scientific | 83 | 2 | 1 | 3 |  | ON HOLD
New | 33 | LAB Equipments | UP823X - Unibloc Performance Balances | 1 | Precision Scientific | 84 | 2 | 1 | 3 |  | ON HOLD
New | 33 | LAB Equipments | 10 MLH Plus - Magnetic Stirrer with Ceramic | 4 | Precision Scientific | 85 | 2 | 1 | 3 |  | ON HOLD
New | 33 | LAB Equipments | RDHO-80-Dry Hot Air Oven (80 Ltrs) with Temperature | 2 | Precision Scientific | 86 | 2 | 1 | 3 |  | ON HOLD
New | 33 | LAB Equipments | ECPH70042S - Bench Ph Meter | 2 | Precision Scientific | 87 | 2 | 1 | 3 |  | ON HOLD
New | 33 | LAB Equipments | LMUC6 - Digital Ultrasonic Cleaner 5 Ltrs | 1 | Precision Scientific | 88 | 2 | 1 | 3 |  | ON HOLD
New | 33 | LAB Equipments | HI98303 - Conductivity Meter Dist 3 Range 0 - 1990 micro-siemens | 5 | Precision Scientific | 89 | 2 | 1 | 3 |  | ON HOLD
New | 33 | LAB Equipments | HI98107 - Phep Waterproof Pocket Ph Tester | 5 | Precision Scientific | 90 | 2 | 1 | 3 |  | ON HOLD
New | 33 | LAB Equipments | Micro Pipette 1000 ul | 2 | Precision Scientific | 91 | 2 | 1 | 3 |  | ON HOLD
New | 33 | LAB Equipments | Micro pipette 20-200 ul | 2 | Precision Scientific | 92 | 2 | 1 | 3 |  | ON HOLD
New | 33 | LAB Equipments | Micro pipette 10-100 ul | 2 | Precision Scientific | 93 | 2 | 1 | 3 |  | ON HOLD
5 | 36 | LAB Equipments | Laboratory Glasswares & titration stands (1 Set) | 1 | Precision Scientific | 94 | 2 | 1 | 3 |  | ON HOLD
New | 28 | LAB Equipments | Mitutoyo Digital Vernier Caliper 0 -300 mm Inch LC 0.01 mm (HSN code: 90173010) | 8 | BTSA | 95 | 1 | 1 | 2 |  | PO Released
New | 28 | LAB Equipments | Mitutoyo Digital Vernier Caliper 0-150 MM L C- 0.01mm (HSN code: 90173010) | 3 | BTSA | 96 | 1 | 1 | 2 |  | PO Released
New | 28 | LAB Equipments | Mitutoyo Digital Depth Gauge 0-10mm (HSN code: 90173010) | 4 | BTSA | 97 | 1 | 1 | 2 |  | PO Released
New | 28 | LAB Equipments | Raytek MT4 infrared thermometer temp -18 to 400 degree celcius (HSN code: 90318000) | 5 | BTSA | 98 | 1 | 1 | 2 |  | PO Released
New | 28 | LAB Equipments | Stech Share A Durometer 0-100 Shore unit (HSN code: 90248091) | 1 | BTSA | 99 | 1 | 1 | 2 |  | PO Released
New | 28 | LAB Equipments | Mitutoyo feeler Gauge set 0.05-1mm length 100mm (HSN code: 90318000) | 3 | BTSA | 100 | 1 | 1 | 2 |  | PO Released
New | 28 | LAB Equipments | Mitutoyo Surface roughnesstester-SJ 220 (HSN code:90178000) | 1 | BTSA | 101 | 1 | 1 | 2 |  | PO Released
New | 28 | LAB Equipments | Tenmars Make sound level meter measuring range 35-130dB (HSN code: 90318000) | 1 | BTSA | 102 | 1 | 1 | 2 |  | PO Released
New | 28 | LAB Equipments | Tenmar Make Vibration tester 1mm to 5mm (HSN code: 90173010) | 2 | BTSA | 103 | 1 | 1 | 2 |  | PO Released
New | 28 | LAB Equipments | Insize make Densitometer(HSN code: 90318000) | 1 | BTSA | 104 | 1 | 1 | 2 |  | PO Released
5 | 29 | Final Inspection | Bow & Twist Inspection Table & Guage --> Jafuji granite surface table with stand 630x630mm (HSN code:9038000) | 1 | BTSA | 105 | 1 | 1 | 2 |  | PO Released
New | 31 | LAB Equipments | Mitutoyo digital outside micrometer 0-25mm LC 0.001 (90173010) | 10 | BTSA | 106 | 1 | 1 | 2 |  | PO Released
New | 31 | LAB Equipments | Microgauges measuring pin dia 0.2 -0.5 step 0.01 (HSN code: 90173029) | 2 | BTSA | 107 | 1 | 1 | 2 |  | PO Released
New | 31 | LAB Equipments | Jafuji Surface roughness meter stand(HSN code: 90318000) | 1 | BTSA | 108 | 1 | 1 | 2 |  | PO Released
New | 31 | LAB Equipments | Jafuji Granite surface table woth stand 630x630mm (HSN code: 90318000) | 1 | BTSA | 109 | 1 | 1 | 2 |  | PO Released
New | 31 | LAB Equipments | Kristeel steel rule 1000cm (HSN code: 90173010) | 5 | BTSA | 110 | 1 | 1 | 2 |  | PO Released
New | 32 | LAB Equipments | Microgauges make Measuring Pin0.5-1.00 mm in step of 0.01mm (HSN code:90173029 ) | 2 | BTSA | 111 | 1 | 1 | 2 |  | PO Released
New | 32 | LAB Equipments | Microgauges make pin gauge Dia1.01-2.50 mm step 0.01mm (HSN code:90173029 ) | 2 | BTSA | 112 | 1 | 1 | 2 |  | PO Released
New | 32 | LAB Equipments | Microgauges Measuring pin rangedia 2.51-4.00 mm in step of 0.01mm (HSN Code:90173029) | 2 | BTSA | 113 | 1 | 1 | 2 |  | PO Released
New | 32 | LAB Equipments | Microgauges Measuring pin rangedia 4.01-5.50 mm in step of 0.01mm (HSN code:90173029 ) | 2 | BTSA | 114 | 1 | 1 | 2 |  | PO Released
New | 32 | LAB Equipments | Microgauges Measuring pin rangedia 5.51-7.00 mm in step of 0.01mm (HSN code:90173029) | 2 | BTSA | 115 | 1 | 1 | 2 |  | PO Released
New | 32 | LAB Equipments | Microgauges make pin gauge Dia7.01-8.00mm step 0.01mm (HSN code:90173029) | 2 | BTSA | 116 | 1 | 1 | 2 |  | PO Released
New | 32 | LAB Equipments | Microgauges make pin gauge Dia0.5-4.00mm step 0.05mm (HSN code:90173029) | 2 | BTSA | 117 | 1 | 1 | 2 |  | PO Released
New | 32 | LAB Equipments | Microgauges make pin gauge Dia4.05-8.00mm step 0.05mm (HSN code:90173029) | 2 | BTSA | 118 | 1 | 1 | 2 |  | PO Released
5 | 30 | LAB Equipments | Refrigerator for Lab Chemical storage --> Bluestar VC325 | 1 | Amazon (Online) | 119 | 0 | 1 | 1 |  | PO Released
New | 33 | LAB Equipments | Electronic Platform Weighing Scale (100 kg capacity) - Make: Microtek Smart | 1 | Amazon (Online) | 120 | 0 | 1 | 1 |  | PO Released

## ManpowerPlanning
Manpower Planning for installation
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## ManpowerSummary
Row Labels | Manpower count1 | Machines | Row Labels | Sum of machine count | Row Labels | Count of Machines
DRILLING | 9 | 7 | Abishake M | 2 | ALTIX | 2
Grand Total | 9 | 7 | Adhithya Ponnupayan | 2 | ANDERSON | 11
|  |  | Ajay | 4 | DYNACHEM | 1
|  |  | Ajith Kumar M |  | GP | 2
|  |  | Ashraf | 2 | KEWEI | 3
|  |  | Avinash B M | 8 | LAUFFER | 1
|  |  | Balamurugan Eswaramoorthy | 4 | PENTAGAL | 1
|  |  | Chinnadurai Kandasamy | 4 | SCHMOLL | 9
|  |  | Devis V | 4 | TAIYO | 1
|  |  | Dhatchanamoorthy R | 4 | UCE | 26
|  |  | Hariharan R | 2 | (blank)
|  |  | Hariharan S | 1 | CIMS | 6
|  |  | John peter S | 2 | Grand Total | 63
|  |  | Kannan K R | 2
|  |  | Karmugil P | 5
|  |  | Kathirvel S | 18
|  |  | Mareeswaran R | 1
|  |  | Mullaikumaran Saravanan | 1
|  |  | Nishanth P | 1
|  |  | Pandiyan | 5
|  |  | Pradhap | 3
|  |  | Rajaselvan | 21
|  |  | Rithik S | 8
|  |  | Sakthivel Annadurai | 7
|  |  | Santhoshkumar R | 2
|  |  | Selvaraj V | 2
|  |  | Soumya Ranjan Swain | 1
|  |  | Srinath | 1
|  |  | Suresh Rathinam | 2
|  |  | Suryaprakash M | 2
|  |  | Suthakar P | 8
|  |  | Tendulkar Venkatachalam | 2
|  |  | Thirumoorthy Selvaraj | 1
|  |  | Vengadesh M | 1
|  |  | Vinoth V | 1
|  |  | Vishakh | 4
|  |  | Viswasurya V | 2
(blank)
|  |  | Mohan Raj M | 3
|  |  | Santhosh P | 1
|  |  | Sudhagar I | 1
|  |  | Shivan M | 1
|  |  | Varshini D | 1
|  |  | AMAL | 26
|  |  | Ragul R | 6
|  |  | Parthiban M | 6
|  |  | Anil Kumar C | 2
|  |  | Gokul D | 2
|  |  | Vishnuram G | 1
|  |  | KEERTHI | 26
|  |  | Vignesh Dhakshnamoorthy | 1
|  |  | Manoj | 64
|  |  | Prasanth P | 2
|  |  | Boopathiajay | 1
|  |  | Harjana Thindappa | 1
|  |  | Rohit Pradhan | 1
|  |  | Sanjay Kumar S | 2
|  |  | Prakash Sakthivel | 2
|  |  | Chandru D | 1
|  |  | Saravanan M | 3
|  |  | Arjunan R | 1
|  |  | Dinesh D | 2
|  |  | Ravi kumar Chaurasiya | 2
|  |  | GANESH | 10
|  |  | Amarnath R | 2
|  |  | ANAND | 11
|  |  | Nishesh | 2
|  |  | Grand Total | 324

## ManpowerPlan
Department | Supplier | Description | Days for completion | Start Date | End date | Team Lead | Primary | Secondary | Tertiary | Quaternary | Manpower count | Manpower | machine count
IMAGING | UCE | PRECLEAN MACHINE FOR PHOTO | 19 | 2026-06-01 | 2026-06-20 | Rithik S | Karmugil P | Mullaikumaran Saravanan | Manoj |  | 1 | Rithik S | 8
IMAGING | UCE | DES | 15 | 2026-06-01 | 2026-06-16 | Rithik S | Karmugil P | Hariharan S | Manoj |  | 1 | Karmugil P | 5
SOLDERMASK | UCE | PRE CLEAN MACHINE SM | 18 | 2026-06-06 | 2026-06-24 | Kathirvel S | Kathirvel S | Vinoth V | GANESH |  | 1 | Kathirvel S | 18
SOLDERMASK | UCE | SM DEVELOPING | 14 | 2026-06-10 | 2026-06-24 | Kathirvel S | Kathirvel S | Ajith Kumar | GANESH |  | 1 | Santhoshkumar R | 2
ML PRESSING | UCE | BOND FILM | 19 | 2026-06-01 | 2026-06-20 | Sakthivel Annadurai | Sakthivel Annadurai | Chinnadurai Kandasamy | AMAL |  | 1 | Sakthivel Annadurai | 7
WET PROCESS | UCE | DEBURRING LINE WITH ULTRASONIC CLEANING AND LOADER / UNLODER | 14 | 2026-06-13 | 2026-06-27 | Suthakar P | Balamurugan Eswaramoorthy | Boopathiajay | Manoj |  | 1 | Devis V | 4
WET PROCESS | UCE | HOIST TYPE DESMEAR + PTH LINE | 14 | 2026-07-04 | 2026-07-18 | Suthakar P | Devis V | Harjana Thindappa | Manoj |  | 1 | Balamurugan Eswaramoorthy | 4
WET PROCESS | UCE | VIAKING LINE FOR DIRECT METALIZATION WITH LOADER & UNLOADER | 15 | 2026-06-01 | 2026-06-16 | Suthakar P | Balamurugan Eswaramoorthy | Suryaprakash M | Manoj |  | 1 | Suryaprakash M | 2
WET PROCESS | UCE | AUTOMATIC VCP PANEL PLATING LINE | 45 | 2026-06-01 | 2026-07-16 | Suthakar P | Balamurugan Eswaramoorthy | Kannan K R | Manoj |  | 1 | Kannan K R | 2
WET PROCESS | UCE | PLASMA DESMEAR MACHINE | 5 | 2026-07-04 | 2026-07-09 | Suthakar P | Devis V | Rohit Pradhan | Manoj |  | 1 | Suthakar P | 8
WET PROCESS | [10 empty] | 1 | Boopathiajay | 1
WET PROCESS | [10 empty] | 1 | Harjana Thindappa | 1
WET PROCESS
WET PROCESS
WET PROCESS | [10 empty] | 1 | Manoj | 16
WET PROCESS | [10 empty] | 1 | Rohit Pradhan | 1
SURFACE FINISH | UCE | FINAL CLEANING LINE | 8 | 2026-06-19 | 2026-06-27 | Avinash B M | Suresh Rathinam | Viswasurya V | AMAL |  | 1 | Suresh Rathinam | 2
SURFACE FINISH | UCE | OSP LINE | 11 | 2026-06-16 | 2026-06-27 | Avinash B M | Selvaraj V | Thirumoorthy Selvaraj | AMAL |  | 1 | Avinash B M | 8
WET PROCESS | UCE | DVCP PATTERN PLATING LINE | 60 | 2026-08-03 | 2026-10-02 | Suthakar P | Devis V | Kannan K R | Manoj
WET PROCESS | UCE | DEBURR + DESMEAR + PTH MACHINE | 45 | 2026-07-13 | 2026-08-27 | Suthakar P | Devis V | Suryaprakash M | Manoj
WET PROCESS | UCE | SES MACHINE | 18 | 2026-07-13 | 2026-08-01 | Suthakar P | Balamurugan Eswaramoorthy | Soumya Ranjan Swain | Manoj |  | 1 | Soumya Ranjan Swain | 1
IMAGING | UCE | INNER LAYER PRETREATMENT MACHINE | 12 | 2026-07-13 | 2026-07-25 | Rithik S | Karmugil P | Adhithya Ponnupayan | Manoj |  | 1 | Mohan Raj M | 3
IMAGING | UCE | INNER LAYER DES MACHINE | 15 | 2026-07-13 | 2026-07-28 | Rithik S | Karmugil P | Santhosh P | Manoj |  | 1 | Santhosh P | 1
IMAGING | UCE | DRY FILM DEVELOPER MACHINE | 9 | 2026-07-17 | 2026-07-29 | Rithik S | Karmugil P | Sudhagar I | Manoj |  | 1 | Sudhagar I | 1
ML PRESSING | UCE | SST PLATE CLEANING MACHINE | 8 | 2026-07-18 | 2026-07-31 | Sakthivel Annadurai | Varshini D | Hariharan R | AMAL |  | 1 | Shivan M | 1
SURFACE FINISH | UCE | IMMERSION TIN | 18 | 2026-07-20 | 2026-08-08 | Avinash B M | Sanjay Kumar S | Saravanan M | AMAL |  | 1 | Sanjay Kumar S | 2
SURFACE FINISH | UCE | IMMERSION GOLD PRE-TREATMENT | 8 | 2026-07-21 | 2026-08-01 | Avinash B M | Suresh Rathinam | Chandru D | AMAL |  | 1 | Prakash Sakthivel | 2
SURFACE FINISH | UCE | IMMERSION GOLD POST-TREATMENT | 7 | 2026-07-22 | 2026-08-03 | Avinash B M | Prakash Sakthivel | Saravanan M | AMAL |  | 1 | Chandru D | 1
SURFACE FINISH | UCE | HAL PRE TREATMENT MACHINE | 10 | 2026-07-24 | 2026-08-05 | Avinash B M | Sanjay Kumar S | Arjunan R | AMAL |  | 1 | Saravanan M | 3
SURFACE FINISH | UCE | HAL POS TTREATMENT MACHINE | 10 | 2026-07-25 | 2026-08-06 | Avinash B M | Prakash Sakthivel | Viswasurya V | AMAL |  | 1 | Arjunan R | 1
ML PRESSING | UCE | LDD BONDFILM MACHINE | 16 | 2026-07-28 | 2026-08-13 | Sakthivel Annadurai | Chinnadurai Kandasamy | Shivan M | AMAL |  | 1 | Varshini D | 1
ML PRESSING | UCE | OXIDE REMOVAL MACHINE | 9 | 2026-07-29 | 2026-08-08 | Sakthivel Annadurai | Chinnadurai Kandasamy | Hariharan R | AMAL |  | 1 | AMAL | 13
AOI | CIMS | AOI SCAN-1 | 2 | 2026-07-13 | 2026-07-15 | Ragul R | Parthiban M | Anil Kumar C | KEERTHI |  | 1 | Ragul R | 6
AOI | CIMS | AOI SCAN-2 | 2 | 2026-07-16 | 2026-07-18 | Ragul R | Parthiban M | Gokul D | KEERTHI |  | 1 | Parthiban M | 6
AOI | CIMS | AOI VERI-1 | 2 | 2026-07-20 | 2026-07-22 | Ragul R | Parthiban M | Vishnuram G | KEERTHI |  | 1 | Anil Kumar C | 2
AOI | CIMS | AOI VERI-2 | 2 | 2026-07-23 | 2026-07-25 | Ragul R | Parthiban M | Vignesh Dhakshnamoorthy | KEERTHI |  | 1 | Gokul D | 2
AOI | CIMS | AOI VERI-3 | 2 | 2026-07-27 | 2026-07-29 | Ragul R | Parthiban M | Anil Kumar C | KEERTHI |  | 1 | Vishnuram G | 1
AOI | [10 empty] | 1 | KEERTHI | 13
AOI | CIMS | AOI VERI-4 | 2 | 2026-07-30 | 2026-08-01 | Ragul R | Parthiban M | Gokul D | KEERTHI |  | 1 | Vignesh Dhakshnamoorthy | 1
IMAGING | DYNACHEM | DRY FILM LAMINATOR | 8 | 2026-06-29 | 2026-07-07 | Rithik S | Mohan Raj M | Adhithya Ponnupayan | Manoj |  | 1 | Mullaikumaran Saravanan | 1
IMAGING | ALTIX | ALTIX | 8 | 2026-07-27 | 2026-08-04 | Rithik S | Mohan Raj M | Vengadesh M | Manoj |  | 1 | Hariharan S | 1
IMAGING | SCHMOLL | MDI | 5 | 2026-07-06 | 2026-07-11 | Rithik S | Mohan Raj M | Nishanth P | Manoj |  | 1 | Adhithya Ponnupayan | 2
IMAGING | [10 empty] | 1 | Vengadesh M | 1
[11 empty] | 1 | Manoj | 16
IMAGING | [10 empty] | 1 | Nishanth P | 1
SOLDERMASK | KEWEI | SCREEN MAKING EQUIPMENT | 5 | 2026-07-14 | 2026-07-19 | Kathirvel S | Kathirvel S | Ravi kumar Chaurasiya | GANESH |  | 1 | Vinoth V | 1
SOLDERMASK | TAIYO | SM PRINTING | 3 | 2026-07-13 | 2026-07-16 | Kathirvel S | Kathirvel S | Dinesh D | GANESH |  | 1 | John peter S | 2
SOLDERMASK | GP | TACK DRYING OVEN | 4 | 2026-07-20 | 2026-07-24 | Kathirvel S | Kathirvel S | Dinesh D | GANESH |  | 1 | Mareeswaran R | 1
SOLDERMASK | ALTIX | ALTIX MACHINE EXPOSING | 6 | 2026-08-10 | 2026-08-16 | Kathirvel S | Kathirvel S | John peter S | GANESH |  | 1 | Ajith Kumar M
SOLDERMASK | SCHMOLL | SCHMOLL MDI EXPOSING | 5 | 2026-07-13 | 2026-07-18 | Kathirvel S | Kathirvel S | John peter S | GANESH |  | 1 | Dinesh D | 2
SOLDERMASK | GP | FINAL CURING OVENS | 4 | 2026-07-27 | 2026-07-31 | Kathirvel S | Kathirvel S | Ajith Kumar | GANESH |  | 1 | Ravi kumar Chaurasiya | 2
SOLDERMASK | KEWEI | LEGEND PRINTING - INKJET | 4 | 2026-07-30 | 2026-08-03 | Kathirvel S | Santhoshkumar R | Ravi kumar Chaurasiya | GANESH |  | 1 | GANESH | 10
SOLDERMASK | KEWEI | LEGEND PRINTING - MANUAL | 4 | 2026-07-10 | 2026-07-14 | Kathirvel S | Santhoshkumar R | Mareeswaran R | GANESH
ML PRESSING | LAUFFER | LAUFFER PRESS | 24 | 2026-06-28 | 2026-07-22 | Sakthivel Annadurai | Sakthivel Annadurai | Chinnadurai Kandasamy | AMAL |  | 1 | Chinnadurai Kandasamy | 4
ML PRESSING | [10 empty] | 1 | Hariharan R | 2
DRILLING | SCHMOLL | CNC DRILLING | 2 | 2026-06-29 | 2026-07-01 | Rajaselvan | Pandiyan | Tendulkar Venkatachalam | KEERTHI |  | 1 | Rajaselvan | 21
DRILLING | SCHMOLL | CNC DRILLING | 2 | 2026-07-02 | 2026-07-04 | Rajaselvan | Rajaselvan | Ashraf | KEERTHI |  | 1 | Pandiyan | 5
DRILLING | SCHMOLL | CNC DRILLING | 2 | 2026-07-05 | 2026-07-07 | Rajaselvan | Nishesh | Abishake M | KEERTHI |  | 1 | Vishakh | 4
DRILLING | SCHMOLL | CNC DRILLING | 2 | 2026-07-08 | 2026-07-10 | Rajaselvan | Vishakh | Srinath | KEERTHI |  | 1 | Abishake M | 2
DRILLING | SCHMOLL | CNC DRILLING | 2 | 2026-07-11 | 2026-07-13 | Rajaselvan | Nishesh | Abishake M | KEERTHI |  | 1 | Tendulkar Venkatachalam | 2
DRILLING | SCHMOLL | CNC DRILLING | 2 | 2026-07-14 | 2026-07-16 | Rajaselvan | Pandiyan | Tendulkar Venkatachalam | KEERTHI |  | 1 | Ashraf | 2
DRILLING | [10 empty] | 1 | KEERTHI | 13
DRILLING | [10 empty] | 1 | Srinath | 1
DRILLING | [10 empty] | 1 | Nishesh | 2
DRILLING | SCHMOLL | CNC DRILLING | 3 | 2026-07-17 | 2026-07-20 | Rajaselvan | Vishakh | Ashraf | KEERTHI
ROUTING | ANDERSON | CNC ROUTING | 2 | 2026-07-06 | 2026-07-08 | Rajaselvan | Rajaselvan | Dhatchanamoorthy R | ANAND
ROUTING | ANDERSON | CNC ROUTING | 1 | 2026-07-09 | 2026-07-10 | Rajaselvan | Pandiyan | Pradhap | ANAND |  | 1 | Amarnath R | 2
ROUTING | ANDERSON | CNC ROUTING | 2 | 2026-07-11 | 2026-07-13 | Rajaselvan | Ajay | Prasanth P | ANAND |  | 1 | Pradhap | 3
ROUTING | ANDERSON | CNC ROUTING | 1 | 2026-07-14 | 2026-07-15 | Rajaselvan | Vishakh | Dhatchanamoorthy R | ANAND |  | 1 | Prasanth P | 2
ROUTING | ANDERSON | CNC ROUTING | 1 | 2026-07-16 | 2026-07-17 | Rajaselvan | Ajay | Amarnath R | ANAND |  | 1 | Dhatchanamoorthy R | 4
ROUTING | ANDERSON | CNC ROUTING | 2 | 2026-07-18 | 2026-07-20 | Rajaselvan | Pandiyan | Pradhap | ANAND |  | 1 | Ajay | 4
ROUTING | ANDERSON | CNC ROUTING | 1 | 2026-07-21 | 2026-07-22 | Rajaselvan | Ajay | Prasanth P | ANAND |  | 1 | ANAND | 11
ROUTING | ANDERSON | CNC ROUTING | 1 | 2026-07-23 | 2026-07-24 | Rajaselvan | Vishakh | Dhatchanamoorthy R | ANAND
ROUTING | ANDERSON | CNC ROUTING | 2 | 2026-07-25 | 2026-07-27 | Rajaselvan | Rajaselvan | Amarnath R | ANAND
ROUTING | ANDERSON | CNC ROUTING | 1 | 2026-07-28 | 2026-07-29 | Rajaselvan | Pandiyan | Pradhap | ANAND
ROUTING | ANDERSON | CNC ROUTING | 1 | 2026-07-30 | 2026-07-31 | Rajaselvan | Ajay | Dhatchanamoorthy R | ANAND
SURFACE FINISH | [10 empty] | 1 | AMAL | 13
SURFACE FINISH | PENTAGAL | HASL | 15 | 2026-07-01 | 2026-07-16 | Avinash B M | Selvaraj V | Saravanan M | AMAL |  | 1 | Selvaraj V | 2
SURFACE FINISH | [10 empty] | 1 | Viswasurya V | 2
[11 empty] | 1 | Manoj | 16
[11 empty] | 1 | Manoj | 16
SURFACE FINISH | [10 empty] | 1 | Thirumoorthy Selvaraj | 1

## FinalSummary
SL No | Department | Machine | Machine arrival date | Installation start | Installation end | Remarks
1 | MEP Readiness |  |  |  | 2026-04-30 | Actual date
2 | CAM |  |  |  | 2026-04-10 | UCAMX License required by April 10th
3 | ARTWORK | FILM PLOTTING | 2026-05-15 | 2026-05-20 | 2026-05-30 | Machine dispatch pending
4 | Photo imaging | UCE-PHOTO | 2026-04-20 | 2026-04-21 | 2026-05-22 | UCE Dispatch pending
5 | Photo imaging | ALTIX-PHOTO | 2026-01-23 | 2026-05-20 | 2026-05-25 | Artwork to be outsourced
6 | Photo imaging | DYNACHEM | 2026-01-23 | 2026-05-04 | 2026-05-12
7 | Photo imaging | SCHMOLL | 2026-03-31 | 2026-05-04 | 2026-05-08
8 | AOI | CIMS | 2026-04-10 | 2026-05-15 | 2026-05-23 | Machine dispatch pending
9 | CNC Drilling | SCHMOLL | 2026-03-31 | 2026-05-04 | 2026-05-21
10 | WET process | UCE-WET | 2026-04-20 | 2026-04-21 | 2026-07-18
11 | SM | ALTIX-SM | 2026-01-23 | 2026-05-20 | 2026-05-25 | Artwork to be outsourced
12 | SM | SCHMOLL-SM | 2026-03-31 | 2026-05-18 | 2026-05-23
13 | SM | UCE-SM | 2026-04-20 | 2026-05-04 | 2026-05-24
14 | SM | OVEN | 2026-05-15 | 2026-05-15 | 2026-05-17 | Machine not yet ordered
15 | SM | SCREEN PRINTING | 2026-04-30 | 2026-05-05 | 2026-05-18 | Screen to be outsourced
16 | SM | LEGEND | 2026-06-15 | 2026-06-16 | 2026-06-18 | Machine not yet ordered
17 | CNC Routing | Anderson | 2026-03-31 | 2026-05-04 | 2026-05-30
18 | SF | UCE-SF | 2026-04-20 | 2026-05-14 | 2026-06-05
19 | SF | HASL | 2026-03-13 | 2026-05-25 | 2026-05-30
20 | BBT | ATG | TBD | TBD | TBD | Machine dispatch pending
21 | FI Readiness |  |  |  | 2026-05-31 | Target date
22 | Ware House |  |  | 2026-04-30 | 2026-04-30 | Target date
23 | Lab |  |  | 2026-04-30 | 2026-04-30 | Target date
24 | RM |  |  | 2026-04-30 | 2026-04-30 | Target date
25 | Collection tank |  |  |  |  | Ready upto 350KL
26 | ETP |  |  |  | 2026-06-02 | Actual date
27 | RO and DI |  |  |  | 2026-04-30 | need to order
Formulas:
Installation end = [Installation start]+5
Installation start = [Machine arrival date]
Installation start = [Machine arrival date]+1

## InstallationPlanBatch1
| Department | Supplier | Description | Activity | Days for completion | Start date | Start Date | End date |  |  |  | UCE | 26 | Other | 5
1 | IMAGING | UCE | PRECLEAN MACHINE FOR PHOTO | INSTALLATION | 13 | 2026-05-06 | 2026-06-06 | 2026-06-19 | - | PRECLEAN MACHINE FOR PHOTO-INSTALLATION | UCE-PRECLEAN MACHINE FOR PHOTO | 2026-06-06 |  |  |  | 57
2 | IMAGING | UCE | PRECLEAN MACHINE FOR PHOTO | LEACHING | 3 | 2026-06-19 | 2026-07-24 | 2026-07-27 | - | PRECLEAN MACHINE FOR PHOTO-LEACHING | UCE-PRECLEAN MACHINE FOR PHOTO
3 | IMAGING | UCE | PRECLEAN MACHINE FOR PHOTO | CHEMICAL TRIALS | 3 | 2026-07-27 | 2026-07-27 | 2026-07-30 | - | PRECLEAN MACHINE FOR PHOTO-CHEMICAL TRIALS | UCE-PRECLEAN MACHINE FOR PHOTO
4 | IMAGING | UCE | PRECLEAN MACHINE FOR PHOTO | TRAINING | 3 | 2026-07-30 | 2026-07-30 | 2026-08-02 | - | PRECLEAN MACHINE FOR PHOTO-TRAINING | UCE-PRECLEAN MACHINE FOR PHOTO
5 | IMAGING | UCE | DES | INSTALLATION | 15 | 2026-05-03 | 2026-06-01 | 2026-06-16 | - | DES-INSTALLATION | UCE-DES | 2026-06-01 |  |  |  | 66
6 | IMAGING | UCE | DES | LEACHING | 5 | 2026-06-16 | 2026-07-25 | 2026-07-30 | - | DES-LEACHING | UCE-DES
7 | IMAGING | UCE | DES | CHEMICAL TRIALS | 4 | 2026-07-30 | 2026-07-30 | 2026-08-03 | - | DES-CHEMICAL TRIALS | UCE-DES
8 | IMAGING | UCE | DES | TRAINING | 3 | 2026-08-03 | 2026-08-03 | 2026-08-06 | - | DES-TRAINING | UCE-DES
9 | SOLDERMASK | UCE | PRE CLEAN MACHINE SM | INSTALLATION | 12 | 2026-05-18 | 2026-06-01 | 2026-06-13 | - | PRE CLEAN MACHINE SM-INSTALLATION | UCE-PRE CLEAN MACHINE SM | 2026-06-01 |  |  |  | 65
10 | SOLDERMASK | UCE | PRE CLEAN MACHINE SM | LEACHING | 3 | 2026-06-13 | 2026-07-27 | 2026-07-30 | - | PRE CLEAN MACHINE SM-LEACHING | UCE-PRE CLEAN MACHINE SM
11 | SOLDERMASK | UCE | PRE CLEAN MACHINE SM | CHEMICAL TRIALS | 3 | 2026-07-30 | 2026-07-30 | 2026-08-02 | - | PRE CLEAN MACHINE SM-CHEMICAL TRIALS | UCE-PRE CLEAN MACHINE SM
12 | SOLDERMASK | UCE | PRE CLEAN MACHINE SM | TRAINING | 3 | 2026-08-02 | 2026-08-02 | 2026-08-05 | - | PRE CLEAN MACHINE SM-TRAINING | UCE-PRE CLEAN MACHINE SM
13 | SOLDERMASK | UCE | SM DEVELOPING | INSTALLATION | 9 | 2026-05-04 | 2026-06-11 | 2026-06-20 | - | SM DEVELOPING -INSTALLATION | UCE- SM DEVELOPING | 2026-06-11 |  |  |  | 58
14 | SOLDERMASK | UCE | SM DEVELOPING | LEACHING | 3 | 2026-06-20 | 2026-07-30 | 2026-08-02 | - | SM DEVELOPING -LEACHING | UCE- SM DEVELOPING
15 | SOLDERMASK | UCE | SM DEVELOPING | CHEMICAL TRIALS | 3 | 2026-08-02 | 2026-08-02 | 2026-08-05 | - | SM DEVELOPING -CHEMICAL TRIALS | UCE- SM DEVELOPING
16 | SOLDERMASK | UCE | SM DEVELOPING | TRAINING | 3 | 2026-08-05 | 2026-08-05 | 2026-08-08 | - | SM DEVELOPING -TRAINING | UCE- SM DEVELOPING
17 | ML PRESSING | UCE | BOND FILM | INSTALLATION | 12 | 2026-05-14 | 2026-06-01 | 2026-06-13 | - | BOND FILM-INSTALLATION | UCE-BOND FILM | 2026-06-01 |  |  |  | 68
18 | ML PRESSING | UCE | BOND FILM | LEACHING | 3 | 2026-06-13 | 2026-07-30 | 2026-08-02 | - | BOND FILM-LEACHING | UCE-BOND FILM
19 | ML PRESSING | UCE | BOND FILM | CHEMICAL TRIALS | 3 | 2026-08-02 | 2026-08-02 | 2026-08-05 | - | BOND FILM-CHEMICAL TRIALS | UCE-BOND FILM
20 | ML PRESSING | UCE | BOND FILM | TRAINING | 3 | 2026-08-05 | 2026-08-05 | 2026-08-08 | - | BOND FILM-TRAINING | UCE-BOND FILM
21 | WET PROCESS | UCE | DEBURRING LINE WITH ULTRASONIC CLEANING AND LOADER / UNLODER | INSTALLATION | 10 | 2026-05-16 | 2026-06-15 | 2026-06-25 | - | DEBURRING LINE WITH ULTRASONIC CLEANING AND LOADER / UNLODER-INSTALLATION | UCE-DEBURRING LINE WITH ULTRASONIC CLEANING AND LOADER / UNLODER | 2026-06-15 |  |  |  | 52
22 | WET PROCESS | UCE | DEBURRING LINE WITH ULTRASONIC CLEANING AND LOADER / UNLODER | LEACHING | 3 | 2026-06-25 | 2026-07-31 | 2026-08-03 | - | DEBURRING LINE WITH ULTRASONIC CLEANING AND LOADER / UNLODER-LEACHING | UCE-DEBURRING LINE WITH ULTRASONIC CLEANING AND LOADER / UNLODER
23 | WET PROCESS | UCE | DEBURRING LINE WITH ULTRASONIC CLEANING AND LOADER / UNLODER | TRAINING | 3 | 2026-08-03 | 2026-08-03 | 2026-08-06 | - | DEBURRING LINE WITH ULTRASONIC CLEANING AND LOADER / UNLODER-TRAINING | UCE-DEBURRING LINE WITH ULTRASONIC CLEANING AND LOADER / UNLODER
24 | WET PROCESS | UCE | HOIST TYPE DESMEAR + PTH LINE | INSTALLATION | 14 |  | 2026-07-13 | 2026-07-27 | - | HOIST TYPE DESMEAR + PTH LINE-INSTALLATION | UCE-HOIST TYPE DESMEAR + PTH LINE | 1900-01-25 |  |  |  | 25
25 | WET PROCESS | UCE | HOIST TYPE DESMEAR + PTH LINE | LEACHING | 3 |  | 2026-07-28 | 2026-07-31 | - | HOIST TYPE DESMEAR + PTH LINE-LEACHING | UCE-HOIST TYPE DESMEAR + PTH LINE
26 | WET PROCESS | UCE | HOIST TYPE DESMEAR + PTH LINE | CHEMICAL TRIALS | 3 |  | 2026-08-01 | 2026-08-04 | - | HOIST TYPE DESMEAR + PTH LINE-CHEMICAL TRIALS | UCE-HOIST TYPE DESMEAR + PTH LINE
27 | WET PROCESS | UCE | HOIST TYPE DESMEAR + PTH LINE | TRAINING | 2 |  | 2026-08-05 | 2026-08-07 | - | HOIST TYPE DESMEAR + PTH LINE-TRAINING | UCE-HOIST TYPE DESMEAR + PTH LINE
28 | WET PROCESS | UCE | VIAKING LINE FOR DIRECT METALIZATION WITH LOADER & UNLOADER | INSTALLATION | 15 | 2026-05-22 | 2026-06-01 | 2026-06-16 | - | VIAKING LINE FOR DIRECT METALIZATION WITH LOADER & UNLOADER-INSTALLATION | UCE-VIAKING LINE FOR DIRECT METALIZATION WITH LOADER & UNLOADER | 2026-06-01 |  |  |  | 72
29 | WET PROCESS | UCE | VIAKING LINE FOR DIRECT METALIZATION WITH LOADER & UNLOADER | LEACHING | 4 | 2026-06-16 | 2026-08-01 | 2026-08-05 | - | VIAKING LINE FOR DIRECT METALIZATION WITH LOADER & UNLOADER-LEACHING | UCE-VIAKING LINE FOR DIRECT METALIZATION WITH LOADER & UNLOADER
30 | WET PROCESS | UCE | VIAKING LINE FOR DIRECT METALIZATION WITH LOADER & UNLOADER | CHEMICAL TRIALS | 4 | 2026-08-05 | 2026-08-05 | 2026-08-09 | - | VIAKING LINE FOR DIRECT METALIZATION WITH LOADER & UNLOADER-CHEMICAL TRIALS | UCE-VIAKING LINE FOR DIRECT METALIZATION WITH LOADER & UNLOADER
31 | WET PROCESS | UCE | VIAKING LINE FOR DIRECT METALIZATION WITH LOADER & UNLOADER | TRAINING | 3 | 2026-08-09 | 2026-08-09 | 2026-08-12 | - | VIAKING LINE FOR DIRECT METALIZATION WITH LOADER & UNLOADER-TRAINING | UCE-VIAKING LINE FOR DIRECT METALIZATION WITH LOADER & UNLOADER
32 | WET PROCESS | UCE | AUTOMATIC VCP PANEL PLATING LINE | INSTALLATION | 45 | 2026-05-01 | 2026-06-01 | 2026-07-16 | - | AUTOMATIC VCP PANEL PLATING LINE-INSTALLATION | UCE-AUTOMATIC VCP PANEL PLATING LINE | 2026-05-31 |  |  |  | 80
33 | WET PROCESS | UCE | AUTOMATIC VCP PANEL PLATING LINE | LEACHING | 7 | 2026-07-16 | 2026-07-31 | 2026-08-07 | - | AUTOMATIC VCP PANEL PLATING LINE-LEACHING | UCE-AUTOMATIC VCP PANEL PLATING LINE
34 | WET PROCESS | UCE | AUTOMATIC VCP PANEL PLATING LINE | CHEMICAL TRIALS | 10 | 2026-08-07 | 2026-08-07 | 2026-08-17 | - | AUTOMATIC VCP PANEL PLATING LINE-CHEMICAL TRIALS | UCE-AUTOMATIC VCP PANEL PLATING LINE
35 | WET PROCESS | UCE | AUTOMATIC VCP PANEL PLATING LINE | TRAINING | 3 | 2026-08-17 | 2026-08-17 | 2026-08-20 | - | AUTOMATIC VCP PANEL PLATING LINE-TRAINING | UCE-AUTOMATIC VCP PANEL PLATING LINE
36 | WET PROCESS | UCE | PLASMA DESMEAR MACHINE | INSTALLATION | 6 |  | 2026-07-13 | 2026-07-19 | - | PLASMA DESMEAR MACHINE-INSTALLATION | UCE-PLASMA DESMEAR MACHINE | 1900-01-25 |  |  |  | 14
37 | WET PROCESS | UCE | PLASMA DESMEAR MACHINE | LEACHING | 1 |  | 2026-07-20 | 2026-07-21 | - | PLASMA DESMEAR MACHINE-LEACHING | UCE-PLASMA DESMEAR MACHINE
38 | WET PROCESS | UCE | PLASMA DESMEAR MACHINE | CHEMICAL TRIALS | 2 |  | 2026-07-22 | 2026-07-24 | - | PLASMA DESMEAR MACHINE-CHEMICAL TRIALS | UCE-PLASMA DESMEAR MACHINE
39 | WET PROCESS | UCE | PLASMA DESMEAR MACHINE | TRAINING | 2 |  | 2026-07-25 | 2026-07-27 | - | PLASMA DESMEAR MACHINE-TRAINING | UCE-PLASMA DESMEAR MACHINE
40 | SURFACE FINISH | UCE | FINAL CLEANING LINE | INSTALLATION | 7 | 2026-06-02 | 2026-06-22 | 2026-06-29 | - | FINAL CLEANING LINE-INSTALLATION | UCE-FINAL CLEANING LINE | 2026-06-22 |  |  |  | 50
41 | SURFACE FINISH | UCE | FINAL CLEANING LINE | LEACHING | 3 | 2026-06-29 | 2026-08-03 | 2026-08-06 | - | FINAL CLEANING LINE-LEACHING | UCE-FINAL CLEANING LINE
42 | SURFACE FINISH | UCE | FINAL CLEANING LINE | CHEMICAL TRIALS | 2 | 2026-08-06 | 2026-08-06 | 2026-08-08 | - | FINAL CLEANING LINE-CHEMICAL TRIALS | UCE-FINAL CLEANING LINE
43 | SURFACE FINISH | UCE | FINAL CLEANING LINE | TRAINING | 3 | 2026-08-08 | 2026-08-08 | 2026-08-11 | - | FINAL CLEANING LINE-TRAINING | UCE-FINAL CLEANING LINE
44 | SURFACE FINISH | UCE | OSP LINE | INSTALLATION | 11 | 2026-05-24 | 2026-06-18 | 2026-06-29 | - | OSP LINE-INSTALLATION | UCE-OSP LINE | 2026-06-18 |  |  |  | 56
45 | SURFACE FINISH | UCE | OSP LINE | LEACHING | 3 | 2026-06-29 | 2026-08-03 | 2026-08-06 | - | OSP LINE-LEACHING | UCE-OSP LINE
46 | SURFACE FINISH | UCE | OSP LINE | CHEMICAL TRIALS | 4 | 2026-08-06 | 2026-08-06 | 2026-08-10 | - | OSP LINE-CHEMICAL TRIALS | UCE-OSP LINE
47 | SURFACE FINISH | UCE | OSP LINE | TRAINING | 3 | 2026-08-10 | 2026-08-10 | 2026-08-13 | - | OSP LINE-TRAINING | UCE-OSP LINE
48 | WET PROCESS | UCE | DVCP PATTERN PLATING LINE | INSTALLATION | 60 |  | 2026-08-03 | 2026-10-02
49 | WET PROCESS | UCE | DVCP PATTERN PLATING LINE | LEACHING | 7 |  | 2026-10-03 | 2026-10-10
50 | WET PROCESS | UCE | DVCP PATTERN PLATING LINE | CHEMICAL TRIALS | 7 |  | 2026-10-11 | 2026-10-18
51 | WET PROCESS | UCE | DVCP PATTERN PLATING LINE | TRAINING | 3 |  | 2026-10-19 | 2026-10-22
52 | WET PROCESS | UCE | DEBURR + DESMEAR + PTH MACHINE | INSTALLATION | 45 |  | 2026-08-03 | 2026-09-17
53 | WET PROCESS | UCE | DEBURR + DESMEAR + PTH MACHINE | LEACHING | 4 |  | 2026-09-18 | 2026-09-22
54 | WET PROCESS | UCE | DEBURR + DESMEAR + PTH MACHINE | CHEMICAL TRIALS | 4 |  | 2026-09-23 | 2026-09-27
55 | WET PROCESS | UCE | DEBURR + DESMEAR + PTH MACHINE | TRAINING | 2 |  | 2026-09-28 | 2026-09-30
56 | WET PROCESS | UCE | SES MACHINE | INSTALLATION | 18 |  | 2026-08-03 | 2026-08-21
57 | WET PROCESS | UCE | SES MACHINE | LEACHING | 3 |  | 2026-08-22 | 2026-08-25
58 | WET PROCESS | UCE | SES MACHINE | CHEMICAL TRIALS | 3 |  | 2026-08-26 | 2026-08-29
59 | WET PROCESS | UCE | SES MACHINE | TRAINING | 2 |  | 2026-08-30 | 2026-09-01
60 | IMAGING | UCE | INNER LAYER PRETREATMENT MACHINE | INSTALLATION | 12 |  | 2026-08-03 | 2026-08-15
61 | IMAGING | UCE | INNER LAYER PRETREATMENT MACHINE | LEACHING | 3 |  | 2026-08-16 | 2026-08-19
62 | IMAGING | UCE | INNER LAYER PRETREATMENT MACHINE | CHEMICAL TRIALS | 3 |  | 2026-08-20 | 2026-08-23
63 | IMAGING | UCE | INNER LAYER PRETREATMENT MACHINE | TRAINING | 2 |  | 2026-08-24 | 2026-08-26
64 | IMAGING | UCE | INNER LAYER DES MACHINE | INSTALLATION | 15 |  | 2026-08-03 | 2026-08-18
65 | IMAGING | UCE | INNER LAYER DES MACHINE | LEACHING | 3 |  | 2026-08-19 | 2026-08-22
66 | IMAGING | UCE | INNER LAYER DES MACHINE | CHEMICAL TRIALS | 3 |  | 2026-08-23 | 2026-08-26
67 | IMAGING | UCE | INNER LAYER DES MACHINE | TRAINING | 2 |  | 2026-08-27 | 2026-08-29
68 | IMAGING | UCE | DRY FILM DEVELOPER MACHINE | INSTALLATION | 9 |  | 2026-08-07 | 2026-08-16
69 | IMAGING | UCE | DRY FILM DEVELOPER MACHINE | LEACHING | 3 |  | 2026-08-17 | 2026-08-20
70 | IMAGING | UCE | DRY FILM DEVELOPER MACHINE | CHEMICAL TRIALS | 3 |  | 2026-08-21 | 2026-08-24
71 | IMAGING | UCE | DRY FILM DEVELOPER MACHINE | TRAINING | 2 |  | 2026-08-25 | 2026-08-27
72 | ML PRESSING | UCE | SST PLATE CLEANING MACHINE | INSTALLATION | 8 |  | 2026-08-08 | 2026-08-16
73 | ML PRESSING | UCE | SST PLATE CLEANING MACHINE | TRAINING | 2 |  | 2026-08-17 | 2026-08-19
74 | SURFACE FINISH | UCE | IMMERSION TIN | INSTALLATION | 18 |  | 2026-08-10 | 2026-08-28
75 | SURFACE FINISH | UCE | IMMERSION TIN | LEACHING | 4 |  | 2026-08-29 | 2026-09-02
76 | SURFACE FINISH | UCE | IMMERSION TIN | CHEMICAL TRIALS | 3 |  | 2026-09-03 | 2026-09-06
77 | SURFACE FINISH | UCE | IMMERSION TIN | TRAINING | 2 |  | 2026-09-07 | 2026-09-09
78 | SURFACE FINISH | UCE | IMMERSION GOLD PRE-TREATMENT | INSTALLATION | 8 |  | 2026-08-11 | 2026-08-19
79 | SURFACE FINISH | UCE | IMMERSION GOLD PRE-TREATMENT | LEACHING | 2 |  | 2026-08-20 | 2026-08-22
80 | SURFACE FINISH | UCE | IMMERSION GOLD PRE-TREATMENT | CHEMICAL TRIALS | 3 |  | 2026-08-23 | 2026-08-26
81 | SURFACE FINISH | UCE | IMMERSION GOLD PRE-TREATMENT | TRAINING | 2 |  | 2026-08-27 | 2026-08-29
82 | SURFACE FINISH | UCE | IMMERSION GOLD POST-TREATMENT | INSTALLATION | 7 |  | 2026-08-12 | 2026-08-19
83 | SURFACE FINISH | UCE | IMMERSION GOLD POST-TREATMENT | LEACHING | 2 |  | 2026-08-20 | 2026-08-22
84 | SURFACE FINISH | UCE | IMMERSION GOLD POST-TREATMENT | CHEMICAL TRIALS | 2 |  | 2026-08-23 | 2026-08-25
85 | SURFACE FINISH | UCE | IMMERSION GOLD POST-TREATMENT | TRAINING | 2 |  | 2026-08-26 | 2026-08-28
86 | SURFACE FINISH | UCE | HAL PRE TREATMENT MACHINE | INSTALLATION | 10 |  | 2026-08-17 | 2026-08-27
87 | SURFACE FINISH | UCE | HAL PRE TREATMENT MACHINE | LEACHING | 2 |  | 2026-08-28 | 2026-08-30
88 | SURFACE FINISH | UCE | HAL PRE TREATMENT MACHINE | CHEMICAL TRIALS | 2 |  | 2026-08-31 | 2026-09-02
89 | SURFACE FINISH | UCE | HAL PRE TREATMENT MACHINE | TRAINING | 2 |  | 2026-09-03 | 2026-09-05
90 | SURFACE FINISH | UCE | HAL POS TTREATMENT MACHINE | INSTALLATION | 10 |  | 2026-08-18 | 2026-08-28
91 | SURFACE FINISH | UCE | HAL POS TTREATMENT MACHINE | LEACHING | 2 |  | 2026-08-29 | 2026-08-31
92 | SURFACE FINISH | UCE | HAL POS TTREATMENT MACHINE | CHEMICAL TRIALS | 2 |  | 2026-09-01 | 2026-09-03
93 | SURFACE FINISH | UCE | HAL POS TTREATMENT MACHINE | TRAINING | 2 |  | 2026-09-04 | 2026-09-06
94 | ML PRESSING | UCE | LDD BONDFILM MACHINE | INSTALLATION | 16 |  | 2026-08-24 | 2026-09-09
95 | ML PRESSING | UCE | LDD BONDFILM MACHINE | LEACHING | 3 |  | 2026-09-10 | 2026-09-13
96 | ML PRESSING | UCE | LDD BONDFILM MACHINE | CHEMICAL TRIALS | 4 |  | 2026-09-14 | 2026-09-18
97 | ML PRESSING | UCE | LDD BONDFILM MACHINE | TRAINING | 3 |  | 2026-09-19 | 2026-09-22
98 | ML PRESSING | UCE | OXIDE REMOVAL MACHINE | INSTALLATION | 9 |  | 2026-08-24 | 2026-09-02
99 | ML PRESSING | UCE | OXIDE REMOVAL MACHINE | LEACHING | 2 |  | 2026-09-03 | 2026-09-05
100 | ML PRESSING | UCE | OXIDE REMOVAL MACHINE | CHEMICAL TRIALS | 2 |  | 2026-09-06 | 2026-09-08
101 | ML PRESSING | UCE | OXIDE REMOVAL MACHINE | TRAINING | 2 |  | 2026-09-09 | 2026-09-11
102 | AOI | CIMS | AOI SCAN-1 | INSTALLATION | 2 |  | 2026-07-27 | 2026-07-29
103 | AOI | CIMS | AOI SCAN-2 | INSTALLATION | 2 |  | 2026-07-30 | 2026-08-01
104 | AOI | CIMS | AOI VERI-1 | INSTALLATION | 2 |  | 2026-08-03 | 2026-08-05
105 | AOI | CIMS | AOI VERI-2 | INSTALLATION | 2 |  | 2026-08-06 | 2026-08-08
106 | AOI | CIMS | AOI VERI-3 | INSTALLATION | 2 |  | 2026-08-10 | 2026-08-12
107 | AOI | CIMS | AOI VERI-4 | INSTALLATION | 2 |  | 2026-08-13 | 2026-08-15
108 | AOI | CIMS | AOI-TRAINING | TRAINING | 2 |  | 2026-08-17 | 2026-08-19
109 | IMAGING | DYNACHEM | DRY FILM LAMINATOR | INSTALLATION | 8 | 2026-05-14 | 2026-07-28 | 2026-08-05 | - | DRY FILM LAMINATOR-INSTALLATION | DYNACHEM-DRY FILM LAMINATOR |  |  | 2026-05-19 |  | 11
110 | IMAGING | DYNACHEM | DRY FILM LAMINATOR | TRAINING | 3 | 2026-05-22 | 2026-08-05 | 2026-08-08 | - | DRY FILM LAMINATOR-TRAINING | DYNACHEM-DRY FILM LAMINATOR
111 | IMAGING | ALTIX | ALTIX | INSTALLATION | 8 | 2026-05-30 | 2026-08-17 | 2026-08-25 | - | ALTIX-INSTALLATION | ALTIX- ALTIX |  |  |  |  | 11
112 | IMAGING | ALTIX | ALTIX | TRAINING | 3 | 2026-06-07 | 2026-08-25 | 2026-08-28 | - | ALTIX-TRAINING | ALTIX- ALTIX
113 | IMAGING | SCHMOLL | MDI | INSTALLATION | 5 | 2026-05-18 | 2026-08-01 | 2026-08-06 | - | MDI-INSTALLATION | SCHMOLL- MDI
114 | IMAGING | SCHMOLL | MDI | TRAINING | 3 | 2026-05-26 | 2026-08-06 | 2026-08-09 | - | MDI-TRAINING | SCHMOLL- MDI
115 | SOLDERMASK | KEWEI | SCREEN MAKING EQUIPMENT | INSTALLATION | 5 | 2026-05-15 | 2026-08-18 | 2026-08-23 | - | SCREEN MAKING EQUIPMENT-INSTALLATION | KEWEI-SCREEN MAKING EQUIPMENT
116 | SOLDERMASK | KEWEI | SCREEN MAKING EQUIPMENT | TRAINING | 3 | 2026-05-20 | 2026-08-23 | 2026-08-26 | - | SCREEN MAKING EQUIPMENT-TRAINING | KEWEI-SCREEN MAKING EQUIPMENT
117 | SOLDERMASK | TAIYO | SM PRINTING | INSTALLATION | 3 | 2026-05-25 | 2026-08-20 | 2026-08-23 | - | SM PRINTING -INSTALLATION | TAIYO-SM PRINTING
118 | SOLDERMASK | TAIYO | SM PRINTING | TRAINING | 2 | 2026-05-27 | 2026-08-23 | 2026-08-25 | - | SM PRINTING -TRAINING | TAIYO-SM PRINTING
119 | SOLDERMASK | GP | TACK DRYING OVEN | INSTALLATION | 4 | 2026-05-26 | 2026-08-19 | 2026-08-23 | - | TACK DRYING OVEN -INSTALLATION | GP-TACK DRYING OVEN
120 | SOLDERMASK | GP | TACK DRYING OVEN | TRAINING | 2 | 2026-05-27 | 2026-08-23 | 2026-08-25 | - | TACK DRYING OVEN -TRAINING | GP-TACK DRYING OVEN
121 | SOLDERMASK | ALTIX | ALTIX MACHINE EXPOSING | INSTALLATION | 6 | 2026-06-07 | 2026-08-29 | 2026-09-04 | - | ALTIX MACHINE EXPOSING -INSTALLATION | ALTIX-ALTIX MACHINE EXPOSING
122 | SOLDERMASK | ALTIX | ALTIX MACHINE EXPOSING | TRAINING | 3 | 2026-06-13 | 2026-09-04 | 2026-09-07 | - | ALTIX MACHINE EXPOSING -TRAINING | ALTIX-ALTIX MACHINE EXPOSING
123 | SOLDERMASK | SCHMOLL | SCHMOLL MDI EXPOSING | INSTALLATION | 5 | 2026-05-27 | 2026-08-10 | 2026-08-15 | - | SCHMOLL MDI EXPOSING -INSTALLATION | SCHMOLL-SCHMOLL MDI EXPOSING
124 | SOLDERMASK | SCHMOLL | SCHMOLL MDI EXPOSING | TRAINING | 3 | 2026-06-02 | 2026-08-15 | 2026-08-18 | - | SCHMOLL MDI EXPOSING -TRAINING | SCHMOLL-SCHMOLL MDI EXPOSING
125 | SOLDERMASK | GP | FINAL CURING OVENS | INSTALLATION | 4 | 2026-05-26 | 2026-08-26 | 2026-08-30 | - | FINAL CURING OVENS-INSTALLATION | GP-FINAL CURING OVENS
126 | SOLDERMASK | GP | FINAL CURING OVENS | TRAINING | 2 | 2026-05-28 | 2026-08-30 | 2026-09-01 | - | FINAL CURING OVENS-TRAINING | GP-FINAL CURING OVENS
127 | SOLDERMASK | KEWEI | LEGEND PRINTING - INKJET | INSTALLATION | 4 | 2026-06-26 | 2026-08-17 | 2026-08-21 | - | LEGEND PRINTING - INKJET-INSTALLATION | KEWEI-LEGEND PRINTING - INKJET
128 | SOLDERMASK | KEWEI | LEGEND PRINTING - INKJET | TRAINING | 3 | 2026-06-28 | 2026-08-21 | 2026-08-24 | - | LEGEND PRINTING - INKJET-TRAINING | KEWEI-LEGEND PRINTING - INKJET
129 | SOLDERMASK | KEWEI | LEGEND PRINTING - MANUAL | INSTALLATION | 4 | 2026-06-26 | 2026-08-17 | 2026-08-21 | - | LEGEND PRINTING - MANUAL-INSTALLATION | KEWEI-LEGEND PRINTING - MANUAL
130 | SOLDERMASK | KEWEI | LEGEND PRINTING - MANUAL | TRAINING | 3 | 2026-06-27 | 2026-09-10 | 2026-09-13 | - | LEGEND PRINTING - MANUAL-TRAINING | KEWEI-LEGEND PRINTING - MANUAL
131 | ML PRESSING | LAUFFER | LAUFFER PRESS | INSTALLATION | 24 | 2026-05-25 | 2026-06-30 | 2026-07-24 | - | LAUFFER PRESS-INSTALLATION | LAUFFER-LAUFFER PRESS
132 | ML PRESSING | LAUFFER | LAUFFER PRESS | TRAINING | 3 | 2026-06-16 | 2026-07-24 | 2026-07-27 | - | LAUFFER PRESS-TRAINING | LAUFFER-LAUFFER PRESS
133 | DRILLING | SCHMOLL | CNC DRILLING-1 | INSTALLATION | 2 | 2026-05-14 | 2026-07-28 | 2026-07-30 | - | CNC DRILLING-1-INSTALLATION | SCHMOLL-CNC DRILLING-1
134 | DRILLING | SCHMOLL | CNC DRILLING-2 | INSTALLATION | 2 | 2026-05-16 | 2026-07-31 | 2026-08-02 | - | CNC DRILLING-2-INSTALLATION | SCHMOLL-CNC DRILLING-2
135 | DRILLING | SCHMOLL | CNC DRILLING-3 | INSTALLATION | 2 | 2026-05-18 | 2026-08-03 | 2026-08-05 | - | CNC DRILLING-3-INSTALLATION | SCHMOLL-CNC DRILLING-3
136 | DRILLING | SCHMOLL | CNC DRILLING-4 | INSTALLATION | 2 | 2026-05-21 | 2026-08-06 | 2026-08-08 | - | CNC DRILLING-4-INSTALLATION | SCHMOLL-CNC DRILLING-4
137 | DRILLING | SCHMOLL | CNC DRILLING-5 | INSTALLATION | 2 | 2026-05-23 | 2026-08-09 | 2026-08-11 | - | CNC DRILLING-5-INSTALLATION | SCHMOLL-CNC DRILLING-5
138 | DRILLING | SCHMOLL | CNC DRILLING-6 | INSTALLATION | 2 | 2026-05-25 | 2026-08-12 | 2026-08-14 | - | CNC DRILLING-6-INSTALLATION | SCHMOLL-CNC DRILLING-6
139 | DRILLING | SCHMOLL | CNC DRILLING-XRAY | INSTALLATION | 3 | 2026-05-28 | 2026-08-15 | 2026-08-18 | - | CNC DRILLING-XRAY-INSTALLATION | SCHMOLL-CNC DRILLING-XRAY
140 | DRILLING | SCHMOLL | CNC DRILLING-T | TRAINING | 7 | 2026-05-31 | 2026-08-19 | 2026-08-26 | - | CNC DRILLING-T-TRAINING | SCHMOLL-CNC DRILLING-T
141 | ROUTING | ANDERSON | CNC ROUTING-1 | INSTALLATION | 2 | 2026-05-14 | 2026-08-02 | 2026-08-04 | - | CNC ROUTING-1-INSTALLATION | ANDERSON-CNC ROUTING-1
142 | ROUTING | ANDERSON | CNC ROUTING-2 | INSTALLATION | 1 | 2026-05-17 | 2026-08-05 | 2026-08-06 | - | CNC ROUTING-2-INSTALLATION | ANDERSON-CNC ROUTING-2
143 | ROUTING | ANDERSON | CNC ROUTING-3 | INSTALLATION | 2 | 2026-05-19 | 2026-08-07 | 2026-08-09 | - | CNC ROUTING-3-INSTALLATION | ANDERSON-CNC ROUTING-3
144 | ROUTING | ANDERSON | CNC ROUTING-4 | INSTALLATION | 1 | 2026-05-22 | 2026-08-10 | 2026-08-11 | - | CNC ROUTING-4-INSTALLATION | ANDERSON-CNC ROUTING-4
145 | ROUTING | ANDERSON | CNC ROUTING-5 | INSTALLATION | 1 | 2026-05-24 | 2026-08-12 | 2026-08-13 | - | CNC ROUTING-5-INSTALLATION | ANDERSON-CNC ROUTING-5
146 | ROUTING | ANDERSON | CNC ROUTING-6 | INSTALLATION | 2 | 2026-05-26 | 2026-08-14 | 2026-08-16 | - | CNC ROUTING-6-INSTALLATION | ANDERSON-CNC ROUTING-6
147 | ROUTING | ANDERSON | CNC ROUTING-7 | INSTALLATION | 1 | 2026-05-29 | 2026-08-17 | 2026-08-18 | - | CNC ROUTING-7-INSTALLATION | ANDERSON-CNC ROUTING-7
148 | ROUTING | ANDERSON | CNC ROUTING-8 | INSTALLATION | 1 | 2026-05-31 | 2026-08-19 | 2026-08-20 | - | CNC ROUTING-8-INSTALLATION | ANDERSON-CNC ROUTING-8
149 | ROUTING | ANDERSON | CNC ROUTING-9 | INSTALLATION | 2 | 2026-06-02 | 2026-08-21 | 2026-08-23 | - | CNC ROUTING-9-INSTALLATION | ANDERSON-CNC ROUTING-9
150 | ROUTING | ANDERSON | CNC ROUTING-10 | INSTALLATION | 1 | 2026-06-05 | 2026-08-24 | 2026-08-25 | - | CNC ROUTING-10-INSTALLATION | ANDERSON-CNC ROUTING-10
151 | ROUTING | ANDERSON | CNC ROUTING-11 | INSTALLATION | 1 | 2026-06-07 | 2026-08-26 | 2026-08-27 | - | CNC ROUTING-11-INSTALLATION | ANDERSON-CNC ROUTING-11
152 | ROUTING | ANDERSON | CNC ROUTING-T | TRAINING | 7 | 2026-06-08 | 2026-08-28 | 2026-09-04 | - | CNC ROUTING-T-TRAINING | ANDERSON-CNC ROUTING-T
153 | SURFACE FINISH | PENTAGAL | HASL | INSTALLATION | 15 |  | 2026-08-31 | 2026-09-15
154 | SURFACE FINISH | PENTAGAL | HASL | TRAINING | 3 |  | 2026-09-16 | 2026-09-19
Formulas:
Start Date = [UCE]
Start Date = [End date, row above]+35
End date = [Start Date]+[Days for completion]
UCE = [Start date]+Q1+5
UCE = [Start date]+Q1-12
Start date = [End date, row above]
Other = [Start date]+S1